## Instructions
Instructions |  | Categories of Risk - these are examples of the sorts of risks that might fall into each category
Use this information to help you populate the Risk Management tab. The team and guide should discuss whether any additional information needs to be included. Beginning with the Systems Level Design Review, this document should be actively managed by the team, and discussed at each design review throughout MSD I and MSD II. As you approach the end of MSD II, your overall level of risk should approach, if not reach, 0. |  | Technical | Scope creep, components don't work as expected, team members lack the skills necessary to do the work, as-fabricated parts differ from design, flawed assumptions
|  | Resource | Schedule (e.g.: parts don't come in on time, machine shop is busy), personnel (e.g.: team member gets sick, travels for an interview), cost (e.g.: components cost more than expected, fabrication must be outsourced), facilities (e.g.: specialized piece of equipment fails, lose access to lab)
|  | Safety | Injury to team, injury to end user, damage to equipment
|  | Environmental | Team must dispose of significant excess material, design requires hazardou materials, selecting a low-cost component that could lead to shorter life and the need for additional purchases, design requires purchase of consummable items for end user
|  | Social | Design choices cause harm to a team member or end user based on social issues (e.g.: loss of confidentiality, contradicts local cultures and customs)
Likelihood scale | Severity scale | “Importance Score” (Likelihood x Severity) – use this to guide your preference for a risk management strategy
1 - This cause is unlikely to happen | 1 - The impact on the project is very minor. We will still meet deliverables on time and within budget, but it will cause extra work. | Prevent | Action will be taken to prevent the cause(s) from occurring in the first place.
2 - This cause could conceivably happen | 2 - The impact on the project is noticeable. We will deliver reduced functionality, go over budget, or fail to meet some of our requirements. | Reduce | Action will be taken to reduce the likelihood of the cause and/or the severity of the effect on the project, should the cause occur
3 - This cause is very likely to happen | 3 - The impact on the project is severe. We will not be able to deliver, or what we deliver will not meet the customer's needs. | Transfer | Action will be taken to transfer the risk to something else. Insurance is an example of this. You purchase an insurance policy that contractually binds an insurance company to pay for your loss in the event of accident. This transfers the financial consequences of the accident to someone else. Your car is still a wreck, of course.
|  | Accept | Low importance risks may not justify any action at all. If they happen, you simply accept the consequences.

## Risk Management
Team #: | P21311 | Team Name: | Mind Controlled Wheelchair
Date: | 2021-02-28 11:02 | Document Owner: | Dawson Hilk
Revision #: | 1
[5 empty] | 1,3,9 | 1,3,9
ID | Category | Risk Item | Effect | Cause | Likelihood | Severity | Importance | Action to Minimize Risk | Owner
| What type of risk is this? | Describe the risk briefly | What is the effect on any or all of the project deliverables if the cause actually happens? | What are the possible cause(s) of this risk? | L | S | L*S | What action(s) will you take (and by when) to prevent, reduce the impact of, and/or transfer the risk of this occurring? | Who is responsible for following through on mitigation?
1 | safety, environmental | The chair could slam into walls. | Time delay to recode | Did not code correctly | 9 | 1 | 9 | Code it right the first time
2 | safety | The user could fall down stairs if we don't code it correctly | Hospitalized user = closed project | Did not code correctly | 1 | 9 | 9 | Code it right the first time
3 | safety | The chair could catch fire from an overheating CPU(cooling) | Would need new CPU or new chair, pushing back deliverable | Did not take in account how hot the CPU might become | 1 | 9 | 9 | Monitoring CPU and doing proper research before hand
4 | safety | What if the user falls out of chair or isn't on board | Hurt user or rogue chair that would need to be coded | Did not code correctly or establish enough safety restraints | 1 | 3 | 3 | Brainstorm ideas to see if we need it or code it
5 | technical | Interface with camera could be troubling and lead to many unforseen issues | Data from camera would need to be trimmed down and less information is gained | Camera output not as expected or behaiving unexpectedly | 3 | 3 | 9 | Test and understand fully the camera outputs and correlation to the world and what calculations need to be done to make it workable
6 | technical | Software to map could be very complex | Maps would need to be thrown out or adapted to be less descript | Mapping data is too large or too complex to keep good data of | 3 | 1 | 3 | Test to understand how camera information is tuned into maps and what calaculations/storage needs to happen
7 | technical | The interface with the chair controls could be unweildy and not be consistent | More testing on how to control the chair and how the chair reacts to inputs would be needed | Chair responds in unwanted or unexpected ways to input | 1 | 1 | 1 | Careful usage of controls and testing to know how they reacts to all combination on inputs
8 | technical | The software to make heading decisions for chair could have many corner cases that lead to catastrophic failures | Corner cases would need to be worked out, time lost | chair makes incorrect or dangerous heading decisions | 9 | 9 | 81 | Document well and test all code for possible scenarios
9 | safety/environment/resource | Campus closing | Project becomes entirely remote | health concerns | 3 | 9 | 27 | Health saftey
10 | resource | we will need a high quality motherboard to execute the path planning algorithms | Path planning is slowed, potentially lagging the user | Lack of research and/or funding | 3 | 3 | 9 | Do more research before deciding on motherboard
11 | technical | the computing done on the cameras is not as much as we would have hoped | More computing in the motherboard, which may not be able to handle it | Lack of research | 1 | 3 | 3 | Do more research before deciding on motherboard
12 | social | We leave out an important feature that a quadriplegic individual would require. | Dis-satisfaction from the end-user | Inability to conduct an interview | 3 | 1 | 3 | Research what we would have interviewed
13 | safety/technical | Chair does not come to a full stop if object in path | Damage to chair | Did not code correctly | 1 | 9 | 9 | Code it correct first and recheck code imediately if issue arises
14 | safety/technical | Over-correction when faces with obstacles | Hurt user or rogue chair | Did not code correctly or camera output issues | 3 | 9 | 27 | Code it correct first and check to ensure cameras dont move
15 | technical/environmental | Lighting with negatively affect the cameras | Inacturate/inconsistant mapping recorded | Lights | 9 | 1 | 9 | Test how lights effect camera prior to implementation
16 | technical | Camera will be bumped/moved | Inacturate/inconsistant mapping recorded, damage to resources | People walking past, objects hit | 9 | 3 | 27 | Securely mount cameras so they cannot move vertically or horizontally
17 | resource | The chair that we have will not be sufficient for what we want to do | Resource and redesign mounting and functionality | Battery, programability, etc. insufficient for our needs | 1 | 3 | 3 | Look at all components early on and determine if anything needs to be changed or added
18
19
20

## Risk V2
Team #: |  | P21311 | Team Name: | Mind Controlled Wheelchair
Date: |  | 2021-02-28 11:02 | Document Owner: | Dawson Hilk
Revision #: |  | 4
[6 empty] | 1,3,9 | 1,3,9
ID | State | Category | Risk Item | Effect | Cause | Likelihood | Severity | Importance | Action to Minimize Risk | Owner
| active | What type of risk is this? | Describe the risk briefly | What is the effect on any or all of the project deliverables if the cause actually happens? | What are the possible cause(s) of this risk? | L | S | L*S | What action(s) will you take (and by when) to prevent, reduce the impact of, and/or transfer the risk of this occurring? | Who is responsible for following through on mitigation?
8 | active | technical | The software to make heading decisions for chair could have many corner cases that lead to catastrophic failures | Corner cases would need to be worked out, time lost | chair makes incorrect or dangerous heading decisions | 9 | 9 | 81 | Document well and test all code for possible scenarios - accept that we may not hit all cases by may
5 | accepted risk | technical | Interface with camera could be troubling and lead to many unforseen issues | Data from camera would need to be trimmed down and less information is gained | Camera output not as expected or behaiving unexpectedly | 9 | 9 | 81 | Test and understand fully the camera outputs and correlation to the world and what calculations need to be done to make it workable
19 | accepted risk | technical | T265 SDK compatanbility, unstable with current version 2.41 - last documented working version was 2.31 | T265 camera could be unusable, loss of localization and mapping | Realsesne SDK issues | 9 | 9 | 81 | try downgrading SDK, adjust goal from complete automation back to pure object avoidance
7 | closed | technical | The interface with the chair controls could be unweildy and not be consistent | More testing on how to control the chair and how the chair reacts to inputs would be needed | Chair responds in unwanted or unexpected ways to input | 9 | 3 | 27 | Implement Physical joystick controller
9 | active | safety/environment/resource | Campus closing | Project becomes entirely remote | health concerns | 9 | 3 | 27 | Health saftey
14 | active | safety/technical | Over-correction when faced with obstacles | Hurt user or rogue chair | Did not code correctly or camera output issues | 3 | 9 | 27 | Start testing in open space, introduce object and verify avoidance turns before doing actual run.
1 | active | safety, environmental | The chair could slam into walls. | Time delay to recode | Did not code correctly | 9 | 1 | 9 | Test first in an open area and introduce "mock walls" such as a solid flat object and see how chair reacts first before introducing it to an actual wall
15 | active | technical/environmental | Lighting with negatively affect the cameras | Inacturate/inconsistant mapping recorded | Lights | 9 | 1 | 9 | Move cameras back more for shading
16 | active | technical | Camera will be bumped/moved | Inacturate/inconsistant mapping recorded, damage to resources | People walking past, objects hit | 3 | 3 | 9 | Replace velcro with bolts
3 | closed | safety | The chair could catch fire from an overheating CPU(cooling) | Would need new CPU or new chair, pushing back deliverable | Did not take in account how hot the CPU might become | 1 | 9 | 9 | Monitoring CPU and doing proper research before hand
2 | active | safety | The user could fall down stairs if we don't code it correctly | Hospitalized user = closed project | Did not code correctly | 1 | 9 | 9 | Stay away from ledges until general movement is verified, then view how ledges are seen with the chair not moving and then introduce detecting while in motion
13 | active | safety/technical | Chair does not come to a full stop if object in path | Damage to chair | Did not code correctly | 1 | 9 | 9 | Check first with a soft object or easily movable object (holding meter stick in view) to see how chair reacts, then move to stationary objects that would commonly be found
12 | closed | social | We leave out an important feature that a quadriplegic individual would require. | Dis-satisfaction from the end-user | Inability to conduct an interview | 3 | 1 | 3 | Research what we would have interviewed
4 | closed | safety | What if the user falls out of chair or isn't on board | Hurt user or rogue chair that would need to be coded | Did not code correctly or establish enough safety restraints | 1 | 3 | 3 | Brainstorm ideas to see if we need it or code it
6 | triggered | technical | Software to map could be very complex | Maps would need to be thrown out or adapted to be less descript | Mapping data is too large or too complex to keep good data of | 9 | 1 | 9 | Test to understand how camera information is turned into maps and what calaculations/storage needs to happen
11 | closed | technical | the computing done on the cameras is not as much as we would have hoped | More computing in the motherboard, which may not be able to handle it | Lack of research | 1 | 3 | 3 | Do more research before deciding on motherboard
17 | closed | resource | The chair that we have will not be sufficient for what we want to do | Resource and redesign mounting and functionality | Battery, programability, etc. insufficient for our needs | 1 | 3 | 3 | Look at all components early on and determine if anything needs to be changed or added
18 | closed | safety | overheating Raspberry Pi (cooling) | Would need better cooling system in RasPi Case | Did not take in account how hot the Pi might become | 1 | 3 | 3 | Adding cooling fan and possible heat sinc
10 | active | resource | we will need a high quality motherboard to execute the path planning algorithms | Path planning is slowed, potentially lagging the user | Lack of research and/or funding | 1 | 3 | 3 | Do more research before deciding on motherboard
20 | triggered | technical | PCB design doesn't allow for desired functionality | requires purchase of new design / prototype | lack of prior research | 9 | 3 | 27
21 | active | technical | integrating ethernet code (python) with camera scripts (C) | Inability to communicate with headset | difference in language | 3 | 1 | 3 | Work towards calling python in C or implement in C
22 | active | technical | too much drift in IMU readings. | Loss of localization. Difficult to find next intersection | depricated cameras | 3 | 9 | 27 | Talk to customer to compromize between devices
23 | active | technical/safety | Too much latency between detecting an object (moving quickly) and determining new path | Cannot turn quick enough to avoid obstacles | inefficient coding | 3 | 3 | 9 | slow down to allow object to pass by; no path alteration
24

## risks ordered
Risks | Likelihood | Severity | Importance
| L | S | L*S
The software to make heading decisions for chair could have many corner cases that lead to catastrophic failures | 9 | 9 | 81
Camera will be bumped/moved | 9 | 3 | 27
Campus closing | 3 | 9 | 27
Over-correction when faces with obstacles | 3 | 9 | 27
The chair could slam into walls. | 9 | 1 | 9
Lighting with negatively affect the cameras | 9 | 1 | 9
Interface with camera could be troubling and lead to many unforseen issues | 3 | 3 | 9
we will need a high quality motherboard to execute the path planning algorithms | 3 | 3 | 9
The user could fall down stairs if we don't code it correctly | 1 | 9 | 9
The chair could catch fire from an overheating CPU(cooling) | 1 | 9 | 9
Chair does not come to a full stop if object in path | 1 | 9 | 9
Software to map could be very complex | 3 | 1 | 3
We leave out an important feature that a quadriplegic individual would require. | 3 | 1 | 3
The chair that we have will not be sufficient for what we want to do | 1 | 3 | 3
What if the user falls out of chair or isn't on board | 1 | 3 | 3
the computing done on the cameras is not as much as we would have hoped | 1 | 3 | 3
The interface with the chair controls could be unweildy and not be consistent | 1 | 1 | 1